## Sheet1
Project Activity | Business Analyst | Project Manager | End User (Representative) | Technical Lead | Technical Team | QA Tester | Executive Sponsor | Project Sponsor
REQ - Validate Scope | R | A | C | I | I | I | C | C
REQ - Schedule Requirements Phase | R | A | C/I | I/C | I | R | I | I
REQ - Assess Organizational (Business) Impact | A/R | I | C | C | I | I | I | C
REQ - Complete Corp Comm. & Training Plan | R | A | C | I | I | I | I/C | C
REQ - Define/Elicit Functional Requirements | A/R | I | R | C | I | I | R | R
REQ - Document / Review Functional Requirements | A/R | I | C | I | I | I | R | R
REQ - Identify and Document Business Issues | A/R | I | C | I | I | I | R | R
REQ - Manage Business Issues | A/R | C/I | C | I/C | I | I | C | C
REQ - Identify Project Issues | R | A/R | R | R | R | R | R | R
REQ - Document Project Issues | C | A/R | I | I | I | I | I | C
REQ - Manage Project Issues | R | A/R | C/I | C | C | C | C/I | R
REQ - Complete Risk Assessment | R | A/R | R | R | R | R | R | R
REQ - Document Risks | I | A/R | I | I | I | I | I | I
REQ - Develop Mitigation & Contingency Plans (If Req.) | R | A/R | R | R | R | R | R | R
REQ - Document Mitigation and Contingency | I | A/R | I | I | I | I | I | I
REQ - Project Communication | R/C | A/R | I | I | I | I | I | C
REQ - Approval of Functional Requirements | R | A/R | I | I | I | R | R | R
DES - Schedule Design Phase
DES - Define Technical Requirements
DES - Document Technical Secifications
DES - Approval of Tech Specs
DES - Issue Management
DES - Risk Management
DES - Project Change Control
CON - Finalize Project Schedule
CON - Complete Dev & Unit Testing
CON - Schedule QA
CON - Develop QA Plan/Cases
CON - Schedule UAT
CON - Develop UAT Test Plan/Cases
CON - Issue Management
CON - Risk Management
CON - Project Change Control
CON - Project Communication
IMP - Complete QA
IMP - Complete UAT
IMP - Issue Management
IMP - Risk Management
IMP - Project Change Control
IMP - Project Communication
IMP - Schedule Management
IMP - Turnover/Change Control Approval
CLO - Complete Project Closure
Responsible - Those who do work to achieve the task. There can be multiple resources responsible.
Accountable - The resource ultimately accountable for the completion of the task. There must be exactly one A specified for each task.
Consulted - Those whose opinions are sought. Two-way communication.
Informed - Those who are kept up-to-date on progress. One-way communication.
Note: Accountable Assumes Control
** Multiple Roles - can be filled by one individual