## Sheet1
Dates Committed | Required Task | BA Milestone | WBS | Task | Start Date | End Date | Estimated Hours | % Complete | Resources | Notes
No | No | No | 1 | <Project Title> | 2009-05-28 08:00 | 2009-07-06 17:00 | 344 hrs
No | Yes | No | 1.1 | Prep Work | 2009-05-28 08:00 | 2009-05-29 17:00 | 16 hrs
No | Yes | No | 1.1.1 | Review Project Scope with Project Sponsor | 2009-05-28 08:00 | 2009-05-28 17:00 | 8 hrs |  | BA
No | Yes | No | 1.1.2 | Create Project Requirements Specification | 2009-05-29 08:00 | 2009-05-29 17:00 | 8 hrs |  | BA | Enter data all known data (Example: Scope and Biz Req from Biz Case)
No | Yes | No | 1.2 | Conduct Stakeholder Analysis | 2009-06-01 08:00 | 2009-06-02 17:00 | 24 hrs
No | Yes | No | 1.2.1 | Determine systems impacted | 2009-06-01 08:00 | 2009-06-01 17:00 | 8 hrs |  | BA | Use Impact Analysis Checklist
No | Yes | No | 1.2.2 | Determine all organizations impacted and their representative | 2009-06-01 08:00 | 2009-06-01 17:00 | 8 hrs |  | BA | Use Stakeholder Analysis Checklist
No | Yes | No | 1.2.3 | Update Stakeholder list in Requirements Specification | 2009-06-02 08:00 | 2009-06-02 17:00 | 8 hrs |  | BA
No | Yes | No | 1.3 | Determine Elicitation and Modeling Techniques | 2009-06-03 08:00 | 2009-06-03 17:00 | 8 hrs |  | BA
No | Yes | No | 1.4 | Elicit Stakeholder Requirements | 2009-06-04 08:00 | 2009-06-09 17:00 | 72 hrs
No | No | No | 1.4.1 | Elicit requirements - Resource Group … | 2009-06-04 08:00 | 2009-06-04 17:00 | 8 hrs |  | BA | Break out elicitation tasks for each stakeholder group
No | No | No | 1.4.2 | Schedule and conduct interviews - Resource Group ... | 2009-06-04 08:00 | 2009-06-04 17:00 | 8 hrs |  | BA | Break out elicitation tasks for each stakeholder group
No | No | No | 1.4.3 | Schedule and conduct workshops - Resouce Groups … | 2009-06-04 08:00 | 2009-06-04 17:00 | 8 hrs |  | BA | Break out elicitation tasks for each stakeholder group
No | No | No | 1.4.4 | Conduct Survey | 2009-06-04 08:00 | 2009-06-09 17:00 | 32 hrs |  |  | Sample Techniques - Add or Delete As Applicable
No | No | No | 1.4.4.1 | Create Questionnaire | 2009-06-04 08:00 | 2009-06-04 17:00 | 8 hrs |  | BA
No | No | No | 1.4.4.2 | Distribute Survey | 2009-06-05 08:00 | 2009-06-05 17:00 | 8 hrs |  | BA
No | No | No | 1.4.4.3 | Collect Survey Responses | 2009-06-08 08:00 | 2009-06-08 17:00 | 8 hrs |  | BA
No | No | No | 1.4.4.4 | Compile Survey Results | 2009-06-09 08:00 | 2009-06-09 17:00 | 8 hrs |  | BA
No | No | No | 1.4.5 | Complete Document Analysis | 2009-06-04 08:00 | 2009-06-04 17:00 | 8 hrs |  | BA
No | No | No | 1.4.6 | Complete Models / Diagrams | 2009-06-04 08:00 | 2009-06-04 17:00 | 8 hrs |  | BA
No | Yes | No | 1.5 | Complete Analysis and Documentation | 2009-06-10 08:00 | 2009-06-17 17:00 | 48 hrs
No | Yes | No | 1.5.1 | Write Use Cases | 2009-06-10 08:00 | 2009-06-10 17:00 | 8 hrs |  | BA
No | Yes | No | 1.5.2 | Complete Draft Requirement Specification | 2009-06-11 08:00 | 2009-06-11 17:00 | 8 hrs |  | BA
No | Yes | No | 1.5.3 | Review Draft Requirements Specification with SME's | 2009-06-12 08:00 | 2009-06-12 17:00 | 8 hrs |  | BA
No | Yes | No | 1.5.4 | Obtain sign-off on Draft Requirements Specification for SME's | 2009-06-15 08:00 | 2009-06-15 17:00 | 8 hrs |  | BA | Does not require "formal approval"
No | Yes | No | 1.5.5 | Review Draft Requirements with Project Sponsor | 2009-06-16 08:00 | 2009-06-16 17:00 | 8 hrs |  | BA
No | Yes | No | 1.5.6 | Obtain sign-off on Draft Requirements Specification for Project sponsor | 2009-06-17 08:00 | 2009-06-17 17:00 | 8 hrs |  | BA | Does not require "formal approval"
No | Yes | Yes | 1.6 | Deliver Draft Requirements Specification to Project Manager | 2009-06-18 08:00 | 2009-06-18 17:00 | 0 hrs
No | Yes | No | 1.7 | Communication Planning | 2009-06-19 08:00 | 2009-06-22 17:00 | 16 hrs
No | No | No | 1.7.1 | Work with Project Sponsor to create Communication and Training Plan | 2009-06-19 08:00 | 2009-06-19 17:00 | 8 hrs |  | BA | The BA must ensure it is addressed - but may not be responsible for writing
No | Yes | No | 1.7.2 | Work with business project team and training to determine training needs | 2009-06-19 08:00 | 2009-06-19 17:00 | 8 hrs |  | BA
No | No | No | 1.7.3 | Submit DRAFT Communication and Training Plan to PM | 2009-06-22 08:00 | 2009-06-22 17:00 | 0 hrs |  |  | Use Tentative "Go Live" Date
No | Yes | No | 1.8 | QA Review and Resolution | 2009-06-19 08:00 | 2009-06-19 17:00 | 8 hrs |  | BA
No | Yes | No | 1.9 | Participate in team walkthrough of Requirements Specification | 2009-06-22 08:00 | 2009-06-22 17:00 | 8 hrs |  | BA
No | Yes | No | 1.10 | Finalize Requirements Specification and sumbit to PM | 2009-06-23 08:00 | 2009-06-23 17:00 | 8 hrs |  | BA
No | No | No | 1.11 | Finalize Communication Planning | 2009-06-24 08:00 | 2009-06-25 17:00 | 24 hrs
No | No | No | 1.11.1 | Finalize Communication & Training Plan and submit PM | 2009-06-24 08:00 | 2009-06-24 17:00 | 8 hrs |  | BA | Project Sponsor may submit - Use baselined "Go Live" Date
No | Yes | No | 1.11.2 | Determine if updates to User Guides are needed | 2009-06-24 08:00 | 2009-06-24 17:00 | 8 hrs |  | BA
No | No | No | 1.11.3 | Facilitate training or communication as required | 2009-06-25 08:00 | 2009-06-25 17:00 | 8 hrs |  | BA | This may not be required for most projects
No | Yes | No | 1.12 | Project Meetings and Support | 2009-06-24 08:00 | 2009-06-24 17:00 | 8 hrs |  | BA | This task will be used to allocate your time through Design, Construction and QA Testing
No | Yes | No | 1.13 | Participate in team walkthrough of Technical Specifications | 2009-06-24 08:00 | 2009-06-24 17:00 | 8 hrs |  | BA
No | Yes | No | 1.14 | User Acceptance Testing | 2009-06-24 08:00 | 2009-06-30 17:00 | 48 hrs
No | No | No | 1.14.1 | Create the UAT Plan | 2009-06-24 08:00 | 2009-06-24 17:00 | 8 hrs |  | BA | If not created check with BA manager
No | Yes | No | 1.14.2 | Participate in Test Plan walkthrough | 2009-06-25 08:00 | 2009-06-25 17:00 | 8 hrs |  | BA
No | Yes | No | 1.14.3 | Write UA Test Cases - Resource Group … | 2009-06-26 08:00 | 2009-06-26 17:00 | 8 hrs |  | BA | Break out UAT tasks for each stakeholder group
No | Yes | No | 1.14.4 | Facilitate UAT - Resource Group … | 2009-06-29 08:00 | 2009-06-29 17:00 | 8 hrs |  | BA
No | Yes | No | 1.14.5 | Track and resolve all open issues / defects | 2009-06-29 08:00 | 2009-06-29 17:00 | 8 hrs |  | BA
No | Yes | No | 1.14.6 | Gain Business Sign-off | 2009-06-30 08:00 | 2009-06-30 17:00 | 8 hrs |  | BA
No | Yes | Yes | 1.15 | Provide Business Sign-off to PM | 2009-07-01 08:00 | 2009-07-01 17:00 | 0 hrs
No | Yes | No | 1.16 | Warranty | 2009-07-02 08:00 | 2009-07-06 17:00 | 48 hrs |  | BA
No | Yes | No | 1.16.1 | Validate product with end users | 2009-07-02 08:00 | 2009-07-02 17:00 | 8 hrs |  | BA
No | Yes | No | 1.16.2 | Track and resolve warranty issues | 2009-07-03 08:00 | 2009-07-03 17:00 | 8 hrs |  | BA
No | Yes | No | 1.16.3 | Participate in Project Lessons Learned and Closure | 2009-07-06 08:00 | 2009-07-06 17:00 | 8 hrs |  | BA
No | Yes | Yes | 1.17 | Project Closed | 2009-05-28 08:00 | 2009-05-28 17:00 | 0 hrs